## read me!
Please read these hints for using in any case! It is abligatory!
This template shall assist your project work and reduce the administration work on it.
It is obligatory to be intriduced to it and use it permanently.
We can not exclude risks by using it. Because if this these notes are obligatory!
The application should only done by experts in Excel.
Only one responsible person should have the rights to change, all others should only able to red in.
You shouldn't remove or add lines or columns. If you wat to you have to do it with high precision and diligence.
Every change, e.g. removing or adding, you have to check and do the necessary changes in all relevant formulas.
For every application the diligence of the user is necessary.
This is implicit for the input, all formulas and checking and interpretation of the outputs.
This template does not reset the project management, but just support the planning and controlling and reporting.
There absolutly no warranty! The complete responsibility for everything within this template is within user!
How to proceed
All celles where you could or should enter information are in a light grey! All others should be protected by password!
Input of frame data into the frame data sheet. Relevant information will be taken from this by other sheets.
Input of project data in sheet overview (see for this sheet overview example).
Hint: The bars will be there automatically if you enter a number higher then zero into the cells.
Input of project into all other sheets.
Take always care of all data in all sheets.

## frame data
project title | project xxx
P-No. | 123456
Customer / Sponsor | company function name
Supplier | company function name
project manager | Mr. / Mrs. P. Macher
project team members | Mr. / Mrs., Mr. / Mrs., Mr. / Mrs., Mr. / Mrs., Mr. / Mrs.,
planned start of the project | xx.xx.20XX
planned end of the project | xx.xx.20XX
budget | 0
…
…
…
Note on B3: Hinweis der pm-experten: Bitte geben Sie in die hellgrau markierten Felder die Rahmendaten des Projekts ein.

## overview
project xxx |  |  | resonsible |  | day / week / month | [17 empty] | SUM per task absolutly | open budget | progress in % |  |  |  | time prognosis | budget prognosis
P-Nr. |  | 123456 | Mr. / Mrs. P. Macher |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |  |  | costs | scope | time | objectives |  |  | Legend:
| sub-project 1 |  | Leader SP 1 | Plan | 10 | 30 | 20 | 50 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170 | -70 | #DIV/0! | 0% | 0% | 0% |  |  | 1 | Yes
|  |  |  | Actual | 0 | 15 | 45 | 30 | 70 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240
|  | WP 1.1 | Leader AP 1.1 | Plan | day / week / month 1: 10; day / week / month 2: 10 | 20 | -10 | 150% | 0% | 0% | 0% |  |  | 2 | No, but small deviation
|  |  |  | Actual | day / week / month 2: 15; day / week / month 3: 15 | 30
|  | WP 1.2 | Leader AP 1.2 | Plan | day / week / month 2: 20; day / week / month 3: 20; day / week / month 4: 20 | 60 | -30 | 150% | 0% | 0% | 0% |  |  | 3 | No, big deviation
|  |  |  | Actual | day / week / month 3: 30; day / week / month 4: 30; day / week / month 5: 30 | 90
|  | WP 1.3 | Leader AP 1.3 | Plan | day / week / month 4: 30; day / week / month 5: 30; day / week / month 6: 30 | 90 | -30 | 133.3% | 0% | 0% | 0%
|  |  |  | Actual | day / week / month 5: 40; day / week / month 6: 40; day / week / month 7: 40 | 120
|  | WP 1.4 | Leader AP 1.4 | Plan | [18 empty] | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 1.5 | Leader AP 1.5 | Plan | [18 empty] | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 1.6 | Leader AP 1.6 | Plan | [18 empty] | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 1.7 | Leader AP 1.7 | Plan | [18 empty] | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
| sub-project 2 |  | Leader SP 2 | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | WP 2.1 | Leader AP 2.1 | Plan | [18 empty] | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 2.2 | Leader AP 2.2 | Plan | [18 empty] | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 2.3 | Leader AP 2.3 | Plan | [18 empty] | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 2.4 | Leader AP 2.4 | Plan | [18 empty] | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 2.5 | Leader AP 2.5 | Plan | [18 empty] | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 2.6 | Leader AP 2.6 | Plan | [18 empty] | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 2.7 | Leader AP 2.7 | Plan | [18 empty] | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
| sub-project 3 |  | Leader SP 3 | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | WP 3.1 | Leader AP 3.1 | Plan | [18 empty] | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 3.2 | Leader AP 3.2 | Plan | [18 empty] | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 3.3 | Leader AP 3.3 | Plan | [18 empty] | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 3.4 | Leader AP 3.4 | Plan | [18 empty] | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 3.5 | Leader AP 3.5 | Plan | [18 empty] | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 3.6 | Leader AP 3.6 | Plan | [18 empty] | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 3.7 | Leader AP 3.7 | Plan | [18 empty] | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
| sub-project 4 |  | Leader SP 4 | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | WP 4.1 | Leader AP 4.1 | Plan | [18 empty] | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 4.2 | Leader AP 4.2 | Plan | [18 empty] | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 4.3 | Leader AP 4.3 | Plan | [18 empty] | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 4.4 | Leader AP 4.4 | Plan | [18 empty] | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 4.5 | Leader AP 4.5 | Plan | [18 empty] | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 4.6 | Leader AP 4.6 | Plan | [18 empty] | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 4.7 | Leader AP 4.7 | Plan | [18 empty] | 0 | 0 | #DIV/0! | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  |  |  | Budget per time unit absolutly | 10 | 30 | 20 | 50 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170
|  |  |  | cumulated budget absolutly | 10 | 40 | 60 | 110 | 140 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170
|  |  |  | Actual costs absolutly | 0 | 15 | 45 | 30 | 70 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | total project progress
|  |  |  | cumulated budget relaltivly to total budget | 5.882% | 23.53% | 35.29% | 64.71% | 82.35% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | open budget | costs | scope | time | objectives
|  |  |  | Actual costs relativly to total budget | 0% | 8.824% | 26.47% | 17.65% | 41.18% | 23.53% | 23.53% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | -70 | #DIV/0! | 0% | 0% | 0%
Note on AE1: will you realise the open scope in the open time?
Note on AF1: will you realise the open scope in with the open budget?

## objectives
| Project: |  | P-No.: |  |  | Mussziel | Project Manager
| project xxx |  | 123456 |  |  | Sollziel | company function name
Kannziel
result (quantitative)
No. | objective descrition | priority | category | planned | actual | in % | remarks
1 |  | 1 |  |  |  | 0% | enter information about changes, deviations, etc.
2 |  | 2 |  |  |  | 0%
3 |  | 3 |  |  |  | 0%
4 |  | 4 |  |  |  | 0%
5 |  | 5 |  |  |  | 0%
6 |  | 6 |  |  |  | 0%
7 |  | 7 |  |  |  | 0%
8 |  | 8 |  |  |  | 0%
9 |  | 9 |  |  |  | 0%
10 |  | 10 |  |  |  | 0%

## stakeholder
| Project: |  | P-No.: |  | project manager:
| project xxx |  | 123456 |  | company function name
No. | Stakeholder | pos. / neg. | Influence / Might | Interests in project | strategy to integrate | saturation degree | remarks
1 | Stakeholder 1
2 | Stakeholder 2
3 | Stakeholder 3
4 | Stakeholder 4
5 | Stakeholder 5
6 | Stakeholder 6
7 | Stakeholder 7
8 | Stakeholder 8
9 | Stakeholder 9
10 | Stakeholder 10

## riks
| Project: |  | P-No.: |  |  | project manager
| project xxx |  | 123456 |  |  | company function name
No. | risks description | p in % | damage in Euro | risk value | risk occoured? | Plan B and other remarks
1 |  | 0% | 0 | 0 | yes / no
2 |  | 0% | 0 | 0 | yes / no
3 |  | 0% | 0 | 0 | yes / no
4 |  | 0% | 0 | 0 | yes / no
5 |  | 0% | 0 | 0 | yes / no
6 |  | 0% | 0 | 0 | yes / no
7 |  | 0% | 0 | 0 | yes / no
8 |  | 0% | 0 | 0 | yes / no
9 |  | 0% | 0 | 0 | yes / no
10 |  | 0% | 0 | 0 | yes / no
Note on C4: p = probality
Note on D4: what is the damage if risk occours?

## contracts
| Project: |  | P-No.: |  | project manager
| project xxx |  | 123456 |  | company function name
No. | duties of customer | date | responsible | progress in % | Claim potencials | remarks
1 |  |  |  | 0%
2 |  |  |  | 0%
3 |  |  |  | 0%
4 |  |  |  | 0%
5 |  |  |  | 0%
6 |  |  |  | 0%
7 |  |  |  | 0%
8 |  |  |  | 0%
9 |  |  |  | 0%
10 |  |  |  | 0%
Nr. | duties of supplier | date | responsible | progress in % | Claim potencials | remarks
1 |  |  |  | 0%
2 |  |  |  | 0%
3 |  |  |  | 0%
4 |  |  |  | 0%
5 |  |  |  | 0%
6 |  |  |  | 0%
7 |  |  |  | 0%
8 |  |  |  | 0%
9 |  |  |  | 0%
10 |  |  |  | 0%

## overview example
project xxx |  |  | Responsible Person |  | day / week / month | [17 empty] | SUM per task absolutly | open budget | progress in % |  |  |  | time prognosis | budget prognosis
P-No. |  | 123456 | Mr. / Mrs. P. Macher |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |  |  | costs | scope | time | objectives |  |  | Legende:
| sub-project 1 |  | Leader SP 1 | Plan | 115 | 190 | 85 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | -5 | 102.1% | 100% | 100% | 100% |  |  | 1 | Yes
|  |  |  | Actual | 0 | 105 | 195 | 95 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 445
|  | WP 1.1 | Leader AP 1.1 | Plan | day / week / month 1: 50; day / week / month 2: 50 | 100 | 10 | 90% | 100% | 100% | 100% | 3 | 1 | 2 | No, but small deviation
|  |  |  | Actual | day / week / month 2: 40; day / week / month 3: 50 | 90
|  | WP 1.2 | Leader AP 1.2 | Plan | day / week / month 1: 10; day / week / month 2: 20 | 30 | 0 | 100% | 100% | 100% | 100% | 2 | 2 | 3 | No, big deviation
|  |  |  | Actual | day / week / month 2: 10; day / week / month 3: 20 | 30
|  | WP 1.3 | Leader AP 1.3 | Plan | day / week / month 2: 20; day / week / month 3: 30; day / week / month 4: 10 | 60 | -10 | 116.7% | 100% | 100% | 100% | 1 | 3
|  |  |  | Actual | day / week / month 3: 20; day / week / month 4: 40; day / week / month 5: 10 | 70
|  | WP 1.4 | Leader AP 1.4 | Plan | day / week / month 2: 15; day / week / month 3: 15 | 30 | 5 | 83.33% | 100% | 100% | 100%
|  |  |  | Actual | day / week / month 3: 10; day / week / month 4: 15 | 25
|  | WP 1.5 | Leader AP 1.5 | Plan | day / week / month 1: 20; day / week / month 2: 20 | 40 | -10 | 125% | 100% | 100% | 100%
|  |  |  | Actual | day / week / month 2: 20; day / week / month 3: 30 | 50
|  | WP 1.6 | Leader AP 1.6 | Plan | day / week / month 1: 35; day / week / month 2: 25 | 60 | 0 | 100% | 100% | 100% | 100%
|  |  |  | Actual | day / week / month 2: 35; day / week / month 3: 25 | 60
|  | WP 1.7 | Leader AP 1.7 | Plan | day / week / month 2: 40; day / week / month 3: 40; day / week / month 4: 40 | 120 | 0 | 100% | 100% | 100% | 100%
|  |  |  | Actual | day / week / month 3: 40; day / week / month 4: 40; day / week / month 5: 40 | 120
| sub-project 2 |  | Leader SP 2 | Plan | 0 | 0 | 30 | 30 | 50 | 100 | 65 | 25 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315 | -5 | 34.29% | 100% | 100% | 100%
|  |  |  | Actual | 0 | 0 | 0 | 25 | 25 | 45 | 100 | 80 | 30 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320
|  | WP 2.1 | Leader AP 2.1 | Plan | day / week / month 3: 10; day / week / month 4: 10 | 20 | 10 | 35% | 100% | 100% | 100%
|  |  |  | Actual | day / week / month 4: 5; day / week / month 5: 5 | 10
|  | WP 2.2 | Leader AP 2.2 | Plan | day / week / month 3: 20; day / week / month 4: 20 | 40 | 0 | 35% | 100% | 100% | 100%
|  |  |  | Actual | day / week / month 4: 20; day / week / month 5: 20 | 40
|  | WP 2.3 | Leader AP 2.3 | Plan | day / week / month 7: 15; day / week / month 8: 15; day / week / month 9: 15 | 45 | 0 | 35% | 100% | 100% | 100%
|  |  |  | Actual | day / week / month 8: 15; day / week / month 9: 15; day / week / month 10: 15 | 45
|  | WP 2.4 | Leader AP 2.4 | Plan | day / week / month 6: 40; day / week / month 7: 40 | 80 | -20 | 35% | 100% | 100% | 100%
|  |  |  | Actual | day / week / month 7: 50; day / week / month 8: 50 | 100
|  | WP 2.5 | Leader AP 2.5 | Plan | day / week / month 5: 30; day / week / month 6: 30 | 60 | 10 | 35% | 100% | 100% | 100%
|  |  |  | Actual | day / week / month 6: 25; day / week / month 7: 25 | 50
|  | WP 2.6 | Leader AP 2.6 | Plan | day / week / month 5: 20; day / week / month 6: 20 | 40 | 0 | 35% | 100% | 100% | 100%
|  |  |  | Actual | day / week / month 6: 20; day / week / month 7: 20 | 40
|  | WP 2.7 | Leader AP 2.7 | Plan | day / week / month 6: 10; day / week / month 7: 10; day / week / month 8: 10 | 30 | -5 | 30% | 100% | 100% | 100%
|  |  |  | Actual | day / week / month 7: 5; day / week / month 8: 15; day / week / month 9: 15 | 35
| sub-project 3 |  | Leader SP 3 | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 160 | 100 | 50 | 0 | 0 | 0 | 0 | 0 | 365 | 365 | 34.29% | 0% | 0% | 0%
|  |  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | WP 3.1 | Leader AP 3.1 | Plan | day / week / month 10: 20; day / week / month 11: 20 | 40 | 40 | 35% | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 3.2 | Leader AP 3.2 | Plan | day / week / month 10: 15; day / week / month 11: 15 | 30 | 30 | 35% | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 3.3 | Leader AP 3.3 | Plan | day / week / month 11: 30; day / week / month 12: 25; day / week / month 13: 25 | 80 | 80 | 35% | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 3.4 | Leader AP 3.4 | Plan | day / week / month 11: 50; day / week / month 12: 50 | 100 | 100 | 35% | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 3.5 | Leader AP 3.5 | Plan | day / week / month 10: 10; day / week / month 11: 10 | 20 | 20 | 35% | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 3.6 | Leader AP 3.6 | Plan | day / week / month 10: 10; day / week / month 11: 10 | 20 | 20 | 35% | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 3.7 | Leader AP 3.7 | Plan | day / week / month 11: 25; day / week / month 12: 25; day / week / month 13: 25 | 75 | 75 | 30% | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
| sub-project 4 |  | Leader SP 4 | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 125 | 65 | 130 | 0 | 375 | 375 | 34.29% | 0% | 0% | 0%
|  |  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | WP 4.1 | Leader AP 4.1 | Plan | day / week / month 14: 15; day / week / month 15: 15 | 30 | 30 | 35% | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 4.2 | Leader AP 4.2 | Plan | day / week / month 14: 10; day / week / month 15: 10 | 20 | 20 | 35% | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 4.3 | Leader AP 4.3 | Plan | day / week / month 15: 20; day / week / month 16: 25; day / week / month 17: 30 | 75 | 75 | 35% | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 4.4 | Leader AP 4.4 | Plan | day / week / month 15: 20; day / week / month 16: 20 | 40 | 40 | 35% | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 4.5 | Leader AP 4.5 | Plan | day / week / month 15: 10 | 10 | 10 | 35% | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 4.6 | Leader AP 4.6 | Plan | day / week / month 14: 30; day / week / month 15: 30 | 60 | 60 | 35% | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  | WP 4.7 | Leader AP 4.7 | Plan | day / week / month 15: 20; day / week / month 16: 20; day / week / month 17: 100 | 140 | 140 | 30% | 0% | 0% | 0%
|  |  |  | Actual | [18 empty] | 0
|  |  |  | Budget per time unit absolutly | 115 | 190 | 115 | 80 | 50 | 100 | 65 | 25 | 15 | 55 | 160 | 100 | 50 | 55 | 125 | 65 | 130 | 0 | 1495
|  |  |  | cumulated budget absolutly | 115 | 305 | 420 | 500 | 550 | 650 | 715 | 740 | 755 | 810 | 970 | 1070 | 1120 | 1175 | 1300 | 1365 | 1495 | 1495
|  |  |  | Actual costs absolutly | 0 | 105 | 195 | 120 | 75 | 45 | 100 | 80 | 30 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | total project progress
|  |  |  | cumulated budget relaltivly to total budget | 7.692% | 20.4% | 28.09% | 33.44% | 36.79% | 43.48% | 47.83% | 49.5% | 50.5% | 54.18% | 64.88% | 71.57% | 74.92% | 78.6% | 86.96% | 91.3% | 100% | 100% |  | open budget | costs | scope | time | objectives
|  |  |  | Actual costs relativly to total budget | 0% | 7.023% | 13.04% | 8.027% | 5.017% | 3.01% | 6.689% | 5.351% | 2.007% | 1.003% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 730 | 51.25% | 50% | 50% | 50%
Note on AE1: will you realise the open scope in the open time?
Note on AF1: will you realise the open scope in with the open budget?